## Summary
Workbook | 09_Privacy_Risk_Register.xlsx
Project | Privacy Impact & Data Handling Risk Assessment: Customer-Facing Reservation Platform
Purpose | Document privacy risk statements, causes, impacts, likelihood, ratings, existing controls, gaps, mitigations, owners, target dates, residual risk, status, and evidence references.
Assessment Lens | Canadian privacy principles with PIPEDA Fair Information Principles used as an alignment framework.
Scope | Reservation, contact, checkout/payment, admin/internal access, email, logging, vendor processing, and change governance workflows.
Important Limitation | This workbook does not claim PIPEDA compliance, legal advice, official PIA completion, regulatory audit, or certification.
Source Context | Sanitized ITGC project evidence, data flow documentation, testing workpapers, access governance review, and privacy assessment artifacts.
Total Risks | 12
High Risks | 4
Medium Risks | 8
Low Risks | 0
Open / Planned Items | 12

## Risk_Register
Risk ID | Related Finding ID | Risk Statement | Data Element / Workflow | Privacy Principle | Cause | Impact | Likelihood | Inherent Risk Score | Risk Rating | Existing Controls | Control Gap | Recommended Mitigation | Owner | Residual Risk | Status | Evidence Reference | Notes
PR-001 | PF-001 | There is a risk that direct customer identifiers may not receive consistent protection because selected fields are encrypted while other comparable identifiable fields remain stored in plaintext. | First name, last name, address, company information / checkout, reservation, contact workflows | Safeguards; Accountability; Limiting Use, Disclosure, and Retention | Field-level protection is applied selectively across personal information fields. | 4 | 4 | 16 | High | Email and contact number are encrypted using AES-256-CBC. | First name, last name, address, and company information may remain plaintext. | Define field-level protection standards for direct identifiers, document encryption coverage, and extend appropriate safeguards based on sensitivity and business need. | Application Owner / Technical Owner | Medium | Planned | EV-001, EV-002 | Use safeguards gap SG-001 as remediation input.
PR-002 | PF-002 | There is a risk that customer personal information may be accessed beyond operational need because formal RBAC and centralized access governance are not implemented. | Reservation records, contact records, order records, payment references / admin and internal access workflow | Accountability; Safeguards; Limiting Use, Disclosure, and Retention | No formal role model, approval workflow, access review, or need-to-know restriction is documented. | 5 | 4 | 20 | High | Some third-party platforms may have their own account-level controls. | Application-level RBAC and centralized access governance are missing. | Define roles, implement RBAC for admin/internal access, document approval and revocation, and perform periodic access reviews. | Business Owner / Application Owner | Medium | Planned | EV-004 | Critical privacy governance risk.
PR-003 | PF-002 | There is a risk that broad developer access may expose customer personal information or sensitive credentials because developers may access database, deployment, source code, and environment configurations. | MongoDB data, environment variables, source code, deployment configuration / technical access workflow | Accountability; Safeguards | Developer access extends across multiple system layers without formal restriction or segregation of duties. | 5 | 4 | 20 | High | .env files are excluded from repository and environment variables are used. | Developer access to credentials and customer data may be broader than necessary. | Restrict production database and environment access, define emergency access, document access owner, and rotate credentials where appropriate. | Application Owner / Technical Owner | Medium | Planned | EV-004 | Connects to secrets and SoD controls.
PR-004 | PF-003 | There is a risk that unauthorized access, modification, export, or deletion of personal information may not be detected because user and administrative activity logging is limited. | Customer records, admin actions, access events / logging and monitoring workflow | Accountability; Safeguards; Challenging Compliance | Logging captures system events but does not provide structured user/admin activity audit trails. | 5 | 4 | 20 | High | Winston logging captures errors, system events, and selected activity. | No dedicated logging for personal information access, export, modification, deletion, or admin actions. | Implement structured logging for access to personal information, admin actions, exports, deletions, permission changes, and log retention. | Technical Owner / Privacy Reviewer | Medium | Planned | EV-005 | Supports incident investigation and challenge handling.
PR-005 | PF-004 | There is a risk that third-party payment processing accountability may be incomplete because Stripe processing boundaries and internally retained payment metadata are not fully documented. | Payment status, Stripe transaction reference, order record, customer identifiers / checkout and payment workflow | Accountability; Openness; Safeguards; Limiting Use, Disclosure, and Retention | Stripe hosted checkout is used but vendor processing documentation and retained internal payment metadata mapping require centralization. | 4 | 3 | 12 | Medium | Stripe hosted checkout processes payment details externally and full cardholder data is not assessed as stored internally. | Vendor processing boundary, access ownership, retained metadata, and evidence tracking are incomplete. | Create Stripe processing record, vendor inventory entry, internal retained payment metadata list, access owner record, and evidence references. | Vendor / Third-Party Owner | Low to Medium | Planned | EV-003, EV-006 | Do not claim Stripe audit or PCI certification.
PR-006 | PF-005 | There is a risk that personal information may be retained longer than necessary because retention periods and deletion triggers are not fully documented across database, email, logs, and payment references. | Reservations, contact messages, orders, payment references, emails, logs / retention workflow | Limiting Use, Disclosure, and Retention; Accountability; Openness | No centralized retention and deletion matrix is documented for key record types. | 4 | 3 | 12 | Medium | Operational records exist for booking, communication, payment reconciliation, and troubleshooting. | Retention periods, deletion triggers, and record owner expectations are incomplete. | Create retention and deletion matrix covering reservations, contact messages, orders, payment references, email records, and logs. | Privacy Reviewer / Business Owner | Medium | Planned | EV-006 | Use no fixed retention period unless supported by policy.
PR-007 | PF-004, PF-006 | There is a risk that vendor accountability evidence may be insufficient because active third-party services are used without centralized vendor review evidence. | Stripe, Gmail SMTP, Cloudinary, Render, GitHub / vendor dependency workflow | Accountability; Safeguards; Openness | Third-party services are active, but formal vendor risk assessment and monitoring evidence are not centralized. | 4 | 3 | 12 | Medium | Vendor platforms provide service-specific functions and may have platform-level controls. | Vendor role, data involved, terms reference, owner, review date, and monitoring notes are incomplete. | Build vendor inventory with privacy notes, data elements, owners, terms references, and periodic review evidence. | Vendor / Third-Party Owner | Medium | Planned | EV-003 | Stripe-specific assessment is handled separately in file 08.
PR-008 | PF-007 | There is a risk that unreviewed application changes may affect personal information handling because changes can be deployed without formal approval, pull request review, or staging validation. | All personal information processed by reservation, contact, checkout, payment, logging, and email workflows / change governance workflow | Accountability; Safeguards | Formal change approval, branch protection, pull request review, and staging validation are not implemented or not evidenced. | 4 | 3 | 12 | Medium | GitHub and Render support source control and deployment workflow. | Changes affecting personal information systems may be deployed without privacy or safeguard review. | Implement pull request review, branch protection, staging validation, deployment evidence, and privacy review for data handling changes. | Application Owner / Technical Owner | Medium | Planned | EV-002, EV-004 | Connects ITGC change risk to privacy safeguards.
PR-009 | PF-005 | There is a risk that contact form free-text submissions may collect unexpected personal information because customers can enter unrestricted message content. | Contact message content / contact form workflow | Limiting Collection; Safeguards; Limiting Use, Disclosure, and Retention | Free-text field may capture information beyond the minimum needed to respond to an inquiry. | 3 | 3 | 9 | Medium | Contact form supports customer inquiry handling. | No documented guidance, minimization note, review process, or retention rule for free-text messages. | Add clear form guidance, avoid requesting sensitive information, review retention, and limit access to contact messages. | Business Owner / Privacy Reviewer | Low to Medium | Planned | EV-001, EV-006 | Good data minimization risk example.
PR-010 | PF-005 | There is a risk that transactional emails may duplicate personal information outside the main database because confirmation or contact emails can include customer and order details. | Email address, name, address, reservation details, order information / email communication workflow | Limiting Use, Disclosure, and Retention; Safeguards; Openness | Transactional email content and mailbox retention are not centrally mapped to database retention rules. | 3 | 3 | 9 | Medium | Gmail SMTP is used for transactional communications. | Email retention, template minimization, and mailbox access governance may be incomplete. | Map personal information in email templates, minimize unnecessary fields, align retention expectations, and include Gmail access in access reviews. | Business Owner / Privacy Reviewer | Low to Medium | Planned | EV-002, EV-006 | Supports email privacy governance.
PR-011 | PF-006 | There is a risk that privacy accountability may be difficult to demonstrate because evidence references, findings, risks, remediation actions, and closure criteria are not fully centralized. | All assessed personal information and evidence records / evidence traceability workflow | Accountability; Challenging Compliance; Safeguards | Privacy evidence is distributed across data models, workflow notes, access reviews, logs, and remediation records. | 3 | 3 | 9 | Medium | Assessment artifacts and sanitized evidence references exist. | A centralized evidence index should link findings, data elements, risks, mitigations, and closure criteria. | Maintain an evidence index and link every risk to source evidence, owner, remediation action, and closure criteria. | Privacy Reviewer | Low | Planned | EV-001, EV-002, EV-003, EV-004, EV-005, EV-006 | Will connect to 11_Evidence_Index.xlsx.
PR-012 | PF-001, PF-003 | There is a risk that logs may contain personal information without documented minimization, masking, access restriction, or retention rules. | System logs, request metadata, payment/reservation activity, CSRF events / logging and monitoring workflow | Safeguards; Limiting Collection; Limiting Use, Disclosure, and Retention | Logs may capture partially masked PII or technical metadata, while log governance is not fully documented. | 3 | 3 | 9 | Medium | Winston logs system-level events and some activity. | Log content minimization, access control, and retention are not fully documented. | Review log fields, avoid unnecessary PII, apply masking, define log access controls, and document log retention. | Technical Owner / Privacy Reviewer | Low to Medium | Planned | EV-005, EV-006 | Balances logging need with minimization.

## Scoring_Methodology
Section | Description
Purpose | Define the qualitative scoring method used in the Privacy Risk Register.
Impact 1 | Minimal privacy impact. Limited operational inconvenience and low sensitivity.
Impact 2 | Low privacy impact. Limited identifiable information and limited exposure.
Impact 3 | Moderate privacy impact. Personal information could be exposed, retained, or accessed beyond expectation.
Impact 4 | Significant privacy impact. Direct identifiers, payment-related metadata, or broad access concerns are involved.
Impact 5 | Severe privacy impact. Sensitive or high-impact personal information exposure, broad unauthorized access, or major accountability failure.
Likelihood 1 | Rare. Control environment makes occurrence unlikely.
Likelihood 2 | Unlikely. Some controls exist but gaps remain.
Likelihood 3 | Possible. Gaps exist and the event could occur under normal operating conditions.
Likelihood 4 | Likely. Control gaps are known and could reasonably lead to occurrence.
Likelihood 5 | Almost certain. Missing controls or repeated exposure make occurrence highly likely.
Risk Score Formula | Impact multiplied by Likelihood.
Risk Rating Rule | High if score is 16 or higher, Medium if score is 8 to 15, Low if score is below 8.
Residual Risk | Directional estimate after recommended mitigation. Not a formal quantitative risk calculation.
Important Limitation | This scoring is for portfolio assessment and privacy risk documentation. It does not certify compliance or represent a regulatory risk model.

## Reference_Lists
List Name | Value
Risk Rating | High
Risk Rating | Medium
Risk Rating | Low
Residual Risk | High
Residual Risk | Medium
Residual Risk | Low
Residual Risk | Low to Medium
Status | Open
Status | Planned
Status | In Progress
Status | Blocked
Status | Closed
Owner | Business Owner
Owner | Application Owner
Owner | Technical Owner
Owner | Privacy Reviewer
Owner | Vendor / Third-Party Owner
Owner | Business Owner / Application Owner
Owner | Application Owner / Technical Owner
Owner | Technical Owner / Privacy Reviewer
Owner | Privacy Reviewer / Business Owner
Owner | Business Owner / Privacy Reviewer
Finding ID | PF-001
Finding ID | PF-002
Finding ID | PF-003
Finding ID | PF-004
Finding ID | PF-005
Finding ID | PF-006
Finding ID | PF-007
PIPEDA Principle | Accountability
PIPEDA Principle | Identifying Purposes
PIPEDA Principle | Consent
PIPEDA Principle | Limiting Collection
PIPEDA Principle | Limiting Use, Disclosure, and Retention
PIPEDA Principle | Accuracy
PIPEDA Principle | Safeguards
PIPEDA Principle | Openness
PIPEDA Principle | Individual Access
PIPEDA Principle | Challenging Compliance

## Evidence_Map
Evidence ID | Evidence Name | Supports Risk Areas | Notes
EV-001 | Sanitized data model reference | Field-level protection, data elements, plaintext/encrypted field distinction | Supports PF-001 and PR-001.
EV-002 | Sanitized application workflow reference | Reservation, checkout, contact, payment, order, email flows | Supports workflow and data flow risks.
EV-003 | Sanitized vendor dependency reference | Stripe, Gmail SMTP, Cloudinary, Render, GitHub, database hosting context | Supports vendor and third-party processing risks.
EV-004 | Sanitized access review reference | Authentication, RBAC, privileged access, access governance, SoD | Supports PF-002 and PR-002/PR-003.
EV-005 | Sanitized logging review reference | Winston logging, missing user/admin activity logging, log governance | Supports PF-003 and PR-004/PR-012.
EV-006 | Sanitized retention review reference | Retention and deletion considerations for records, email, logs, payment references | Supports PF-005 and related risks.