## Summary
Workbook | 07_Privacy_Safeguards_Gap_Log.xlsx
Project | Privacy Impact & Data Handling Risk Assessment: Customer-Facing Reservation Platform
Purpose | Document privacy safeguard gaps, affected data, privacy impact, related PIPEDA principles, evidence references, owners, target dates, and remediation status.
Primary Lens | PIPEDA Fair Information Principles used as an assessment framework, not a compliance claim.
Source Context | Sanitized ITGC data flow, testing workpapers, access control analysis, walkthrough, and evidence references.
Scope Note | This workbook supports the privacy safeguards review and remediation planning process.
Limitation | This workbook is not a formal legal opinion, official PIA, regulatory audit, certification, or compliance attestation.
Total Gaps | 12
High Risk Gaps | 5
Medium Risk Gaps | 7
Low Risk Gaps | 0
Open Gaps | 11
In Progress Gaps | 1
Closed Gaps | 0

## Safeguards_Gap_Log
Gap ID | Gap Title | Safeguard Area | Affected Data Element | Current State | Expected Privacy Safeguard | Privacy Impact | Related PIPEDA Principle | Risk Rating | Recommended Action | Owner | Target Date | Evidence Reference | Status
SG-001 | Inconsistent Field-Level Protection for Direct Identifiers | Encryption / Data Protection | First name, last name, address, company information, email address, contact number | Email address and contact number are protected with field-level encryption, while first name, last name, address, and company information may remain stored in plaintext. | Comparable direct identifiers should receive documented and consistent protection based on sensitivity, business need, and technical feasibility. | Identifiable customer data may be exposed with uneven safeguards, increasing privacy impact if database access or credential compromise occurs. | Safeguards; Accountability; Limiting Use, Disclosure, and Retention | High | Define field-level protection requirements for direct identifiers, document encryption coverage, and remediate plaintext storage where appropriate. | Application Owner | 46265 | EV-001, EV-002 | Open
SG-002 | No Customer Authentication Context for Booking and Checkout Actions | Authentication / Identity Context | Reservation details, checkout information, order records, payment status | Customers can browse, submit booking or checkout information, and complete transaction-related steps without a customer login or identity verification step. | The application should document whether authentication is required for the business model and implement appropriate controls where attribution, account access, or record changes require identity assurance. | Transaction-related activity may be less attributable to a verified customer identity, which can weaken accountability for record changes, disputes, or suspicious activity review. | Accountability; Safeguards | Medium | Document the authentication decision, identify workflows that require authenticated access, and implement authentication where customer record access or modification is introduced. | Application Owner | 46280 | EV-002, EV-004 | Open
SG-003 | RBAC Not Implemented for Internal Access to Personal Information | Access Control / RBAC | Reservation records, contact records, order records, payment references, customer identifiers | No formal role-based access control model is implemented for internal or administrative access. | Access to personal information should be limited by role, business purpose, and need-to-know. | Internal users or technical personnel may access more personal information than necessary, increasing unauthorized access and internal misuse risk. | Safeguards; Accountability; Limiting Use, Disclosure, and Retention | High | Define privacy-relevant roles, implement RBAC for administrative access, restrict access by data category, and document approval and revocation procedures. | Security / IT Reviewer | 46265 | EV-004 | Open
SG-004 | Broad Developer Privileged Access Across System Layers | Privileged Access Management | MongoDB records, environment variables, source code, deployment configuration, customer PII | Developer access may include GitHub, Render deployment configuration, environment variables, and direct or indirect MongoDB access. | Privileged access should be restricted, approved, monitored, and periodically reviewed based on operational need. | Broad technical access increases the impact of credential misuse, accidental exposure, or inappropriate access to customer personal information. | Accountability; Safeguards | High | Limit production database and secrets access, separate development and administrative duties, require approval for privileged access, and perform periodic access reviews. | Security / IT Reviewer | 46265 | EV-004 | Open
SG-005 | Limited Logging for User and Administrative Activity | Logging / Monitoring | Access to customer records, admin actions, record changes, exports, deletion events | Winston-based system logging exists, but no structured logging was identified for user access, authentication events, or administrative actions. | Access, modification, export, deletion, and permission changes involving personal information should be logged with sufficient detail for investigation. | Unauthorized or inappropriate access to personal information may be difficult to detect, investigate, or evidence. | Accountability; Safeguards; Challenging Compliance | High | Implement structured audit logging for personal information access, admin activity, exports, deletions, and permission changes. Define log retention and review procedures. | Application Owner | 46295 | EV-005 | Open
SG-006 | Secrets Access Not Sufficiently Restricted | Secrets Management | Database connection strings, encryption keys, Stripe keys, email credentials, Cloudinary keys | Sensitive credentials are stored in environment variables and excluded from source code, but access to those secrets may be broad through local or deployment environments. | Secrets should be stored securely with least-privilege access, rotation procedures, access review, and separation from unnecessary users. | Broad access to credentials may enable unauthorized database, vendor, or email access and increase breach exposure for personal information. | Safeguards; Accountability | High | Restrict secrets access, document key ownership, rotate credentials where appropriate, and maintain evidence of who can access production secrets. | Security / IT Reviewer | 46280 | EV-004 | Open
SG-007 | Third-Party Processing Documentation Incomplete | Vendor / Third-Party Processing | Payment status, Stripe transaction reference, email records, media dependency records, hosting metadata | Stripe, Gmail, Cloudinary, Render, GitHub, and database hosting dependencies are used, but vendor processing roles and due diligence evidence are not centralized. | Third-party processing should be documented, including vendor role, data involved, retained internal data, access ownership, and review evidence. | Vendor processing boundaries may be unclear, limiting transparency, accountability, and evidence readiness. | Accountability; Openness; Safeguards; Limiting Use, Disclosure, and Retention | Medium | Create a vendor processing register, document Stripe data boundary, map Gmail/email data handling, and maintain vendor review evidence. | Vendor / Third-Party Owner | 46310 | EV-003 | Open
SG-008 | Retention and Deletion Rules Not Fully Documented | Retention / Deletion | Reservations, contacts, orders, payment references, email records, logs | Retention periods and deletion triggers are not fully documented across database collections, email records, payment references, and logs. | Retention periods, deletion triggers, and exceptions should be documented for each record category and data location. | Personal information may be retained longer than necessary or inconsistently across systems. | Limiting Use, Disclosure, and Retention; Accountability; Openness | Medium | Create a retention and deletion matrix for reservations, contacts, orders, payment references, emails, and logs. Define deletion triggers and exception handling. | Business Owner | 46326 | EV-006 | Open
SG-009 | Unreviewed Changes May Affect Personal Information Systems | Change Governance | Application workflows, reservation records, payment flow, logging, safeguards, retention logic | Code changes may be committed directly to the main branch and deployed without formal pull request review, approval workflow, or staging validation. | Changes affecting personal information processing should be reviewed, approved, tested, and documented before production deployment. | Unreviewed changes may alter data collection, storage, access, logging, third-party processing, or safeguards without privacy review. | Accountability; Safeguards | Medium | Implement branch protection, pull request review, staging validation, and privacy impact review for changes affecting data handling. | Application Owner | 46295 | EV-002, EV-004 | Open
SG-010 | Free-Text Contact Message May Collect Unexpected Personal Information | Data Minimization / Collection Control | Contact message content | Contact form message content is free text and may include unexpected or unnecessary personal information submitted by customers. | Free-text collection should include clear purpose language, avoid encouraging unnecessary sensitive information, and support appropriate retention and review. | The system may collect more personal information than needed for inquiry response, increasing retention and exposure risk. | Limiting Collection; Identifying Purposes; Safeguards; Limiting Use, Disclosure, and Retention | Medium | Add clear contact form guidance, review whether message fields need limits or notices, and define retention rules for resolved inquiries. | Privacy Reviewer | 46310 | EV-001, EV-002, EV-006 | Open
SG-011 | Transactional Emails May Duplicate Personal Information Outside the Database | Email / Communication Safeguards | Name, email, phone number, address, reservation details, order confirmation details, contact message content | Gmail SMTP is used for transactional emails and may create additional copies of customer personal information in email records. | Email templates should minimize unnecessary personal information and email retention should align with documented business needs. | Personal information may be duplicated across email records with unclear retention, access, and minimization controls. | Limiting Use, Disclosure, and Retention; Safeguards; Openness | Medium | Inventory email templates, document data included in each email type, minimize unnecessary fields, and define email retention expectations. | Business Owner | 46326 | EV-003, EV-006 | Open
SG-012 | Privacy Evidence Traceability Not Centralized | Evidence / Accountability | All assessed personal information and related workflows | Privacy-relevant findings, evidence references, vendor notes, retention notes, and remediation actions are not centralized in one evidence structure. | Privacy findings should be traceable to evidence, affected data elements, risk ratings, remediation actions, and closure criteria. | Weak evidence traceability may limit the ability to demonstrate accountability, support remediation, or respond to privacy questions. | Accountability; Challenging Compliance; Safeguards | Medium | Maintain an evidence index linking data elements, findings, gap IDs, evidence references, remediation actions, and closure criteria. | Privacy Reviewer | 46265 | EV-001, EV-002, EV-003, EV-004, EV-005, EV-006 | In Progress

## Reference_Lists
Safeguard Area | Risk Rating | Status | Owner | PIPEDA Principle | Finding ID
Access Control / RBAC | High | Open | Application Owner | Accountability | PF-001 Inconsistent Field-Level Protection
Authentication / Identity Context | Medium | In Progress | Business Owner | Identifying Purposes | PF-002 RBAC / Access Limitation Gap
Change Governance | Low | Closed | Privacy Reviewer | Consent | PF-003 Limited Audit Logging
Data Minimization / Collection Control |  | Deferred | Security / IT Reviewer | Limiting Collection | PF-004 Stripe Third-Party Processing Dependency
Email / Communication Safeguards |  |  | Vendor / Third-Party Owner | Limiting Use, Disclosure, and Retention | PF-005 Retention / Deletion Documentation Incomplete
Encryption / Data Protection |  |  |  | Accuracy | PF-006 Evidence Traceability Gap
Evidence / Accountability |  |  |  | Safeguards | PF-007 Change Management Risk for Systems Handling Personal Information
Logging / Monitoring |  |  |  | Openness
Privileged Access Management |  |  |  | Individual Access
Retention / Deletion |  |  |  | Challenging Compliance
Secrets Management
Vendor / Third-Party Processing

## Evidence_Map
Evidence ID | Evidence Name | Supports | Related Safeguard Areas
EV-001 | Sanitized data model reference | Personal information fields and field-level protection differences | Encryption / Data Protection; Data Minimization
EV-002 | Sanitized application workflow reference | Reservation, checkout, contact, and payment workflow mapping | Authentication; Change Governance; Data Flow
EV-003 | Sanitized vendor dependency reference | Stripe, Gmail, Cloudinary, Render, GitHub, and database dependencies | Vendor / Third-Party Processing; Email
EV-004 | Sanitized access review reference | Privileged access, RBAC gap, access governance observations | Access Control / RBAC; Privileged Access; Secrets Management
EV-005 | Sanitized logging review reference | Winston logs and lack of user/admin activity logging | Logging / Monitoring; Accountability
EV-006 | Sanitized retention review reference | Retention and deletion considerations across records and logs | Retention / Deletion; Evidence / Accountability