## Summary
Privacy Impact & Data Handling Risk Assessment: Customer-Facing Reservation Platform
10_Remediation_Tracker.xlsx
Purpose | Track remediation actions for privacy risks and safeguards gaps identified in the assessment. | Priority | Count | Status | Count
Scope | Access governance, safeguards, logging, vendor processing, retention, change governance, evidence traceability, incident readiness. | High | 8 | Proposed | 17
Important limitation | This tracker documents proposed remediation actions only. It does not certify implementation or legal compliance. | Medium | 9 | Not Started | 0
Total remediation items | 17 | Low | 0 | In Progress | 0
High priority | 8 |  |  | Blocked | 0
Medium priority | 9 |  |  | Closed | 0
Low priority | 0
Proposed status | 17
Open or in progress | 0
Charter alignment note
This remediation tracker aligns with the project charter by converting privacy findings into trackable actions with priority, owner, target date, status, evidence required, closure criteria, and follow-up notes. It avoids compliance certification language and remains a sanitized portfolio artifact.
No real customer data, credentials, confidential production screenshots, vendor contracts, or proprietary implementation details are included.
Remediation items are proposed actions based on privacy-relevant interpretation of system and control observations. Closure requires evidence and review.

## Remediation_Tracker
Remediation ID | Related Risk / Finding | Affected Workflow | Related Data Element | Recommended Action | Privacy Principle | Priority | Owner | Status | Evidence Required | Closure Criteria | Follow-Up Notes | Evidence Reference
RM-001 | PR-001 / PF-001 | Reservation, checkout, contact | First name, last name, address, company information | Define documented field-level protection requirements for direct identifiers and determine which fields require encryption, masking, access restriction, or compensating safeguards. | Safeguards; Accountability | High | Privacy Reviewer / Technical Owner | Proposed | Field protection standard; updated data inventory; technical review note | Protection requirements are documented for each direct identifier and mapped to safeguards or approved compensating controls. | Confirm whether address and company fields require encryption or alternative safeguards based on sensitivity and use. | EV-001, EV-002
RM-002 | PR-001 / PF-001 | MongoDB data storage | First name, last name, address, company information | Review plaintext direct identifier fields and update the data model or storage approach to apply appropriate protection consistently across comparable personal information fields. | Safeguards | High | Technical Owner | Proposed | Updated data model evidence; encryption or masking test evidence | Selected direct identifier fields have documented protection, technical test evidence, and privacy reviewer sign-off. | Do not claim full encryption coverage until validated through testing evidence. | EV-001
RM-003 | PR-002 / PF-002 | Admin / internal access | Reservation records, contact records, order records, payment references | Define privacy-relevant access roles for customer records and document need-to-know access for reservation, contact, order, payment reference, and logging data. | Accountability; Safeguards; Limiting Use, Disclosure, and Retention | High | Application Owner / Privacy Reviewer | Proposed | Access role matrix; role description document | Access roles, permitted data categories, and business justification are documented and approved. | This is documentation and design remediation first, not proof that RBAC has been technically enforced. | EV-004
RM-004 | PR-002 / PF-002 | Admin / internal access | Customer records and admin functions | Implement RBAC or equivalent access restriction for administrative functions that allow access to personal information. | Safeguards; Accountability | High | Technical Owner / Application Owner | Proposed | RBAC configuration evidence; route protection evidence; access test evidence | Admin functions require authenticated and authorized access based on documented roles. | Technical implementation should be tested before marking closed. | EV-004
RM-005 | PR-003 / PF-002 | Developer privileged access | Database records, environment variables, deployment configuration | Restrict developer privileged access to production database, environment variables, deployment settings, and customer data based on documented operational need. | Accountability; Safeguards | High | Application Owner / Technical Owner | Proposed | Privileged access review; access revocation or restriction evidence | Developer access is reviewed, approved, restricted where possible, and documented with business justification. | If full restriction is not practical, compensating monitoring and approval controls should be documented. | EV-004
RM-006 | PR-003 / PF-002 | Access governance | Stripe, Gmail, Cloudinary, GitHub, Render, MongoDB | Create a periodic access review process covering application data, database access, deployment access, source control, and third-party platforms. | Accountability; Safeguards | Medium | Business Owner / Application Owner | Proposed | Access review template; completed sample review; exception log | A review process exists and records access owner, role, business need, review result, and remediation actions. | Include Founder and Developer access across third-party platforms. | EV-004
RM-007 | PR-004 / PF-003 | Logging / monitoring | Customer record access events and admin actions | Implement structured logging for access to personal information, administrative actions, exports, deletions, and permission changes. | Accountability; Safeguards; Challenging Compliance | High | Technical Owner | Proposed | Logging configuration evidence; sample sanitized log entries | Logs capture privacy-relevant access and administrative actions without unnecessary personal information. | Logging should support investigation but avoid creating excessive personal information in logs. | EV-005
RM-008 | PR-012 / PF-003 | Logging / monitoring | Application logs and technical metadata | Define log retention, access restriction, and minimization rules for system logs that may contain personal information or technical metadata. | Limiting Use, Disclosure, and Retention; Safeguards | Medium | Technical Owner / Privacy Reviewer | Proposed | Log retention note; log minimization review; access restriction evidence | Log retention period, access roles, minimization controls, and deletion trigger are documented. | Coordinate with incident investigation needs before reducing log retention. | EV-005, EV-006
RM-009 | PR-005 / PF-004 | Checkout / payment | Payment status, Stripe transaction reference, order record | Create a Stripe processing record documenting business purpose, data elements processed externally, data retained internally, access owner, and evidence references. | Accountability; Openness; Limiting Use, Disclosure, and Retention | Medium | Vendor / Third-Party Owner / Privacy Reviewer | Proposed | Stripe processing record; vendor inventory entry | Stripe processing boundary and internal retained payment metadata are documented and linked to evidence. | This does not audit Stripe internal controls. | EV-003
RM-010 | PR-007 / PF-004 | Vendor processing | Stripe, Gmail, Cloudinary, Render, GitHub | Create a vendor inventory with privacy-relevant data processing notes, business purpose, access owner, and review frequency for active third-party services. | Accountability; Openness; Safeguards | Medium | Vendor / Third-Party Owner | Proposed | Vendor inventory; terms reference log; review notes | Each active vendor has a documented role, data involvement, owner, and evidence reference. | Avoid claiming formal vendor audit unless reviewed evidence supports it. | EV-003
RM-011 | PR-006 / PF-005 | Retention and deletion | Reservations, contacts, orders, payment references, emails, logs | Create a retention and deletion matrix for reservation records, contact messages, order records, payment references, email records, and logs. | Limiting Use, Disclosure, and Retention; Accountability; Openness | High | Privacy Reviewer / Business Owner | Proposed | Retention matrix; deletion trigger documentation | Retention category, business purpose, deletion trigger, exception handling, and owner are documented for each record type. | Do not invent legal retention periods without source support. | EV-006
RM-012 | PR-009 / PF-005 | Contact form | Contact message content | Review contact form instructions and fields to reduce unnecessary free-text personal information collection. | Limiting Collection; Safeguards | Medium | Privacy Reviewer / Application Owner | Proposed | Updated form copy; data minimization review note | Contact form includes clear instructions limiting unnecessary sensitive or unrelated personal information. | Free-text fields cannot be fully controlled, so monitoring and retention remain relevant. | EV-002, EV-006
RM-013 | PR-010 / PF-005 | Email communication | Transactional emails and inquiry responses | Review transactional email templates to minimize unnecessary personal information and align email retention expectations with database retention rules. | Limiting Use, Disclosure, and Retention; Safeguards | Medium | Business Owner / Privacy Reviewer | Proposed | Email template review; email retention note | Email templates use only necessary data and email retention expectations are documented. | Include order confirmations, contact replies, and checkout-related notifications. | EV-002, EV-006
RM-014 | PR-008 / PF-007 | Change management | Application workflows processing personal information | Implement privacy review checkpoints for changes affecting personal information collection, storage, access, retention, logging, or vendor processing. | Accountability; Safeguards | Medium | Application Owner / Technical Owner | Proposed | Change review checklist; pull request review evidence; deployment approval evidence | Changes affecting personal information include review evidence before production deployment. | This supplements technical change management and does not replace full SDLC controls. | EV-002
RM-015 | PR-003 / PF-001, PF-002 | Secrets management | Stripe keys, database credentials, email credentials, Cloudinary keys | Restrict access to secrets, document secret owners, review deployment environment access, and rotate credentials where appropriate. | Safeguards; Accountability | High | Technical Owner | Proposed | Secrets access review; credential owner list; rotation evidence where applicable | Secrets access is limited, documented, and reviewed with evidence of owner and access justification. | Do not include actual secrets in evidence artifacts. | EV-004
RM-016 | PR-011 / PF-006 | Evidence traceability | All assessed privacy findings and remediation records | Centralize privacy evidence references linking data elements, findings, risk statements, remediation actions, owners, status, and closure criteria. | Accountability; Challenging Compliance; Safeguards | Medium | Privacy Reviewer | Proposed | Evidence index; remediation tracker; finding-to-evidence mapping | Each remediation item links to supporting evidence and has documented closure criteria. | This remediation is closed only when 11_Evidence_Index.xlsx is completed and cross-referenced. | EV-001, EV-002, EV-003, EV-004, EV-005, EV-006
RM-017 | PR-004 / PF-003 | Incident readiness | Affected personal information, logs, access paths, vendor events | Create a privacy incident triage template covering affected data, safeguards involved, access path, containment action, real risk of significant harm awareness, and evidence preservation. | Accountability; Safeguards; Challenging Compliance | Medium | Privacy Reviewer / Business Owner | Proposed | Privacy incident triage template; breach recordkeeping note | Incident triage fields are documented and connected to logs, evidence, and remediation actions. | This is not a claim that a full breach response program is implemented. | EV-005, EV-006

## Reference_Lists
Priority | Status | Owner | Privacy Principle | Evidence ID | Finding ID | Finding Title
High | Proposed | Privacy Reviewer | Accountability | EV-001 | PF-001 | Inconsistent Field-Level Protection
Medium | Not Started | Business Owner | Identifying Purposes | EV-002 | PF-002 | RBAC / Access Limitation Gap
Low | In Progress | Application Owner | Consent | EV-003 | PF-003 | Limited Audit Logging
| Blocked | Technical Owner | Limiting Collection | EV-004 | PF-004 | Stripe Third-Party Processing Dependency
| Closed | Vendor / Third-Party Owner | Limiting Use, Disclosure, and Retention | EV-005 | PF-005 | Retention / Deletion Documentation Incomplete
| Deferred | Privacy Reviewer / Business Owner | Accuracy | EV-006 | PF-006 | Evidence Traceability Gap
|  | Application Owner / Technical Owner | Safeguards |  | PF-007 | Change Management Risk for Systems Handling Personal Information
|  | Privacy Reviewer / Technical Owner | Openness
Challenging Compliance

## Evidence_Map
Evidence ID | Evidence Name | Supports Remediation Area | Notes
EV-001 | Sanitized data model reference | Field-level protection, data model review, encryption coverage | Supports remediation for PF-001 and direct identifier protection.
EV-002 | Sanitized application workflow reference | Reservation, contact, checkout, payment, email, change review | Supports workflow and data flow based remediation actions.
EV-003 | Sanitized vendor dependency reference | Stripe, Gmail, Cloudinary, Render, GitHub, database hosting | Supports vendor inventory and processing boundary actions.
EV-004 | Sanitized access review reference | RBAC, privileged access, access reviews, secrets access | Supports access governance and secrets remediation actions.
EV-005 | Sanitized logging review reference | User/admin activity logging, log retention, incident investigation | Supports logging and incident readiness remediation actions.
EV-006 | Sanitized retention review reference | Retention/deletion matrix, email records, logs, payment references | Supports retention and deletion remediation actions.